|  |  |
| --- | --- |
|  | Moving Picture, Audio and Data Coding by Artificial Intelligence  www.mpai.community |

|  |  |
| --- | --- |
| **Public Document** | |
| **N182** | 2021/03/17 |
| **Source** | General Assembly (MPAI-6) |
| **Title** | MPAI Timeline |
| **Target** | MPAI Members |

|  |  |
| --- | --- |
| NB1 | Dates in italic indicate estimated dates |
| NB2 | The UC-FR date refers to the date the GA promotes an area to Functional Requirements stage, etc. |
| NB3 | .. in a date indicate that only the month is estimated |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Acron.** | **Title** | **UC-FR** | **FR-CR** | **CR-CT** | **CT-SD** | **CT-MS** |
| MPAI-AIF | AI Framework | 20/10/21 | 20/11/18 | 20/12/16 | 21/02/17 | *21/07/19* |
| MPAI-CAE | Context-based Audio Enhancement | 20/10/21 | 20/12/16 | 21/02/17 | *21/04/14* | *21/09/15* |
| MPAI-MMC | Multi-Modal Conversation | 20/10/21 | 20/12/16 | 21/02/17 | *21/04/14* | *21/09/15* |
| MPAI-CUI | Compression and Understanding of Industrial Data | 20/11/18 | 21/02/17 | 21/03/17 | *21/05/12* | *21/10/13* |
| MPAI-GSA | Integrative AI-based Analysis of Genomic/ Sensor Experiments | 20/10/21 | 21/04/14 | 21/05/12 | 21/07/19 | *21/12/08* |
| MPAI-SPG | Server-based Predictive Multiplayer Gaming | 20/10/21 | *21/04/14* | *21/05/12* | *21/07/19* | *21/12/08* |
| MPAI-EVC | AI-Enhanced Video Coding | 20/10/21 |  |  |  |  |